## Gantchart
GANTT CHART Mini Project | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE: Car Sales System | [6 empty] | DEPARTMENT NAME: Information Technology
PROJECT GUIDE: Ms.Anagha Aher | [6 empty] | DATE: 08-12-2021
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [24 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
WEEK 1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Rohin Ambati Prathamesh Lambate Sarthak More Kaushal Nikam | 2021-09-15 | 2021-09-20 | 1 | 100% | bar: WEEK 1 F to WEEK 2 F
WEEK 2 | Identifying the technology stack and functionalities of the Mini Project | Sarthak More Kaushal Nikam | 2021-09-20 | 2021-09-27 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F
WEEK 3 | Discussing the project topic with the help of paper prototype. | Rohin Ambati Prathamesh Lambate | 2021-09-30 | 2021-10-06 | 1 | 100% | bar: WEEK 2 W to WEEK 3 W
WEEK 4 | Presentation I | Rohin Ambati Prathamesh Lambate Sarthak More Kaushal Nikam | 2019-10-14 | 2021-10-14 | 0 | 100% | bar: WEEK 2 W to WEEK 3 R
2 | Project Design and Implementation
WEEK 5 | Designing the Graphical User Interface(GUI) | Prathamesh Lambate Sarthak More | 2021-10-02 | 2021-10-30 | 4 | 100% | bar: WEEK 2 W to WEEK 3 R
WEEK 6 | Database Design | Rohin Ambati Kaushal Nikam | 2021-10-27 | 2021-11-03 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 M to WEEK 4 R
WEEK 7 | Database Connectivity with front end | Prathamesh Lambate Sarthak More | 2021-11-04 | 2021-11-15 | 2 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 F to WEEK 5 F
WEEK 8 | Results and Report Writing | Rohin Ambati Kaushal Nikam | 2021-11-20 | 2021-11-30 | 2 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 6 M to WEEK 7 F
WEEK 9 | Presentation II | Rohin Ambati Prathamesh Lambate Sarthak More Kaushal Nikam | 2021-12-03 | 2021-12-03 | 0 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 8 M to WEEK 9 F